# Project Plan

# Prompt

Can you create a project plan and consider:

- We will have 4 developers

- Create the major epics that would be needed

- Timelines and major milestone

- Stake holders needed

# Response

# Inventory Management System – Project Plan

# 1. Project Overview

## Objective

Build a web-based Inventory Management System (IMS) that enables:

- Product and inventory tracking

- Real-time stock updates

- Warehouse operations management

- Supplier and purchase management

- Reporting and audit tracking

# 2. Project Team Structure

## Core Development Team (4 Developers)

| Role | Responsibility |
| --- | --- |
| Tech Lead / Senior Full Stack Developer | Architecture, code reviews, backend leadership |
| Backend Developer | APIs, business logic, database integration |
| Frontend Developer | UI/UX implementation |
| Full Stack Developer | Shared frontend/backend features, integrations |

## Additional Stakeholders

| Stakeholder | Responsibility |
| --- | --- |
| Product Owner | Business decisions and prioritization |
| Business Analyst | Requirements gathering and documentation |
| Project Manager / Scrum Master | Sprint planning and delivery tracking |
| QA Engineer | Testing and quality validation |
| DevOps Engineer | CI/CD, environments, deployments |
| Warehouse Manager | Workflow validation |
| Inventory Operations Team | User acceptance testing |
| IT/Security Team | Security and infrastructure review |

# 3. Recommended Delivery Model

## Methodology

Agile Scrum

## Sprint Duration

2 Weeks

## Total Estimated Duration

20 Weeks

# 4. Major Project Phases

| Phase | Duration |
| --- | --- |
| Discovery & Planning | 2 Weeks |
| Architecture & Design | 2 Weeks |
| Core Development | 10 Weeks |
| Integration & QA | 3 Weeks |
| UAT & Stabilization | 2 Weeks |
| Production Deployment | 1 Week |

# 5. Major Epics

# Epic 1 – Project Setup & Foundation

## Objective

Establish development standards, infrastructure, and project structure.

## Features

- Repository setup

- CI/CD pipeline

- Environment setup

- Authentication framework

- Logging framework

- Error handling

- Base UI framework

## Estimated Duration

2 Weeks

## Assigned Team

- Tech Lead

- Full Stack Developer

# Epic 2 – Authentication & User Management

## Objective

Provide secure access and role-based permissions.

## Features

- Login/logout

- Password reset

- JWT/session management

- Role-based access control

- User management

- Audit logging

## Estimated Duration

2 Weeks

## Dependencies

Project setup completed

# Epic 3 – Product Management

## Objective

Manage inventory catalog and master data.

## Features

- Product CRUD

- Category management

- SKU generation

- Barcode support

- Product search/filtering

## Estimated Duration

2 Weeks

# Epic 4 – Inventory Management

## Objective

Track inventory quantities and movements.

## Features

- Real-time stock tracking

- Multi-warehouse support

- Inventory ledger

- Stock validation

- Inventory history

## Estimated Duration

3 Weeks

# Epic 5 – Stock Inward Management

## Objective

Manage incoming inventory workflows.

## Features

- Goods receiving

- Purchase receiving

- Partial receiving

- Damaged goods tracking

- Supplier stock intake

## Estimated Duration

2 Weeks

# Epic 6 – Stock Outward & Dispatch

## Objective

Handle stock deductions and dispatch operations.

## Features

- Dispatch workflow

- Stock deduction

- Returns handling

- Transfer management

- Dispatch validation

## Estimated Duration

2 Weeks

# Epic 7 – Supplier & Purchase Order Management

## Objective

Manage suppliers and procurement workflows.

## Features

- Supplier management

- Purchase order creation

- Approval workflow

- PO status tracking

## Estimated Duration

2 Weeks

# Epic 8 – Reporting & Dashboard

## Objective

Provide operational visibility and analytics.

## Features

- Inventory summary dashboard

- Low stock reports

- Stock movement reports

- Inventory valuation

- Export to Excel/PDF

## Estimated Duration

2 Weeks

# Epic 9 – Alerts & Notifications

## Objective

Notify users about critical inventory events.

## Features

- Low stock alerts

- Expiry alerts

- Email notifications

- In-app notifications

## Estimated Duration

1 Week

# Epic 10 – QA, Performance & Security Hardening

## Objective

Ensure system quality and production readiness.

## Features

- Functional testing

- Integration testing

- Performance optimization

- Security testing

- Bug fixing

- Regression testing

## Estimated Duration

3 Weeks

# 6. Suggested Sprint Plan

# Sprint 0 (Week 1–2)

## Focus

Planning & Foundation

## Deliverables

- Requirements finalized

- Architecture completed

- Dev environments ready

- Repository setup

- CI/CD setup

# Sprint 1 (Week 3–4)

## Focus

Authentication + Base UI

## Deliverables

- Login/logout

- RBAC

- User management

- Base frontend layout

# Sprint 2 (Week 5–6)

## Focus

Product Management

## Deliverables

- Product CRUD

- Categories

- SKU management

- Product search

# Sprint 3 (Week 7–8)

## Focus

Inventory Management

## Deliverables

- Stock tracking

- Warehouse support

- Inventory ledger

# Sprint 4 (Week 9–10)

## Focus

Stock Inward & Supplier Management

## Deliverables

- Goods receiving

- Supplier module

- Purchase orders

# Sprint 5 (Week 11–12)

## Focus

Stock Outward & Transfers

## Deliverables

- Dispatch workflow

- Returns

- Transfers

# Sprint 6 (Week 13–14)

## Focus

Reporting & Notifications

## Deliverables

- Dashboard

- Reports

- Alerts

# Sprint 7 (Week 15–16)

## Focus

System Integration & Bug Fixes

## Deliverables

- Integrated workflows

- Major defect fixes

# Sprint 8 (Week 17–18)

## Focus

QA & UAT

## Deliverables

- UAT testing

- Performance testing

- Security validation

# Sprint 9 (Week 19–20)

## Focus

Deployment & Hypercare

## Deliverables

- Production deployment

- User training

- Go-live support

# 7. Major Milestones

| Milestone | Timeline |
| --- | --- |
| Requirements Signoff | End of Week 2 |
| Architecture Finalized | End of Week 2 |
| MVP Ready | End of Week 10 |
| Feature Complete | End of Week 14 |
| QA Complete | End of Week 18 |
| UAT Signoff | End of Week 18 |
| Production Go-Live | Week 20 |

# 8. Recommended Developer Allocation

| Area | Primary Owner |
| --- | --- |
| Backend APIs | Backend Developer |
| Frontend UI | Frontend Developer |
| Database & Architecture | Tech Lead |
| Integrations & Shared Features | Full Stack Developer |

# 9. Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Scope expansion | Freeze MVP scope |
| Delayed approvals | Weekly stakeholder demos |
| Inventory accuracy issues | Strong audit logs & validations |
| Performance bottlenecks | Early load testing |
| Security vulnerabilities | Security reviews each sprint |

# 10. MVP Recommendation

## Phase 1 (Must Have)

- Authentication

- Product management

- Inventory tracking

- Stock inward/outward

- Reporting

- Audit logs

## Phase 2 (Nice to Have)

- Barcode scanning

- Mobile support

- ERP integrations

- AI forecasting

- RFID support

# 11. Suggested Success Metrics

| Metric | Target |
| --- | --- |
| Inventory accuracy | >98% |
| System uptime | 99.9% |
| Response time | <3 seconds |
| UAT approval | 100% |
| Critical defects in production | Minimal/Zero |